## Sheet1
GhostQuant™ Plan of Action and Milestones (POA&M)
Weakness ID | Control ID | Weakness Description | Severity | Mitigation Plan | Milestones | Responsible Role | Scheduled Completion | Current Status | Notes
POA&M-001 | IA-5 | MFA not enforced for all API users | Medium | Implement MFA requirement for all API authentication methods | 1) Update API auth module (Week 1) 2) Test MFA integration (Week 2) 3) Deploy to production (Week 3) 4) User notification and training (Week 4) | DevSecOps Lead | 2026-02-28 | In Progress | 60% complete - API module updated
POA&M-002 | SC-12 | Automated key rotation not fully implemented | Medium | Implement automated 365-day key rotation for all encryption keys | 1) Design rotation workflow (Week 1) 2) Implement rotation automation (Week 2-3) 3) Test rotation procedures (Week 4) 4) Deploy and monitor (Week 5) | Cloud Infrastructure Manager | 2026-03-15 | In Progress | 40% complete - Design phase
POA&M-003 | AC-2 | Incomplete access review documentation for Q4 2025 | Low | Complete access review documentation and implement quarterly review automation | 1) Complete Q4 2025 review (Week 1) 2) Document review process (Week 2) 3) Automate review reminders (Week 3) | Compliance Officer | 2026-01-31 | In Progress | 80% complete - Documentation in progress
POA&M-004 | IR-2 | Incomplete IR tabletop exercises for 2025 | Medium | Conduct IR tabletop exercise and schedule quarterly exercises for 2026 | 1) Plan tabletop scenario (Week 1) 2) Conduct exercise (Week 2) 3) Document lessons learned (Week 3) 4) Schedule 2026 exercises (Week 4) | Incident Response Commander | 2026-02-15 | Not Started | Scheduled for January 2026
POA&M-005 | CP-4 | Annual contingency plan testing not completed for 2025 | Medium | Complete annual contingency plan testing and document results | 1) Plan test scenario (Week 1) 2) Execute test (Week 2) 3) Analyze results (Week 3) 4) Update contingency plan (Week 4) | Cloud Infrastructure Manager | 2026-01-31 | In Progress | Test scheduled for January 15, 2026
POA&M-006 | PS-3 | Background screening not completed for 2 contractors | High | Complete background screening for all contractor personnel | 1) Initiate screening requests (Week 1) 2) Follow up with screening vendor (Week 2) 3) Review results and approve access (Week 3) | CISO | 2026-01-15 | In Progress | Screening in progress
POA&M-007 | RA-5 | Vulnerability remediation SLA exceeded for 3 medium-severity findings | Medium | Remediate outstanding vulnerabilities and improve remediation process | 1) Remediate 3 outstanding vulnerabilities (Week 1) 2) Review remediation SLAs (Week 2) 3) Implement automated remediation tracking (Week 3) | DevSecOps Lead | 2026-01-31 | In Progress | 2 of 3 vulnerabilities remediated
POA&M-008 | AU-6 | Automated audit log analysis not fully implemented | Low | Enhance UltraFusion AI™ audit log analysis capabilities | 1) Define analysis use cases (Week 1) 2) Implement analysis algorithms (Week 2-3) 3) Test and validate (Week 4) 4) Deploy to production (Week 5) | DevSecOps Lead | 2026-03-01 | Not Started | Planned for Q1 2026
POA&M-009 | CM-6 | Configuration drift detected on 5 production instances | Medium | Remediate configuration drift and enhance drift detection | 1) Remediate drift on 5 instances (Week 1) 2) Implement automated drift remediation (Week 2) 3) Enhance monitoring and alerting (Week 3) | Cloud Infrastructure Manager | 2026-02-15 | In Progress | 3 of 5 instances remediated
POA&M-010 | SA-11 | Penetration testing not completed for 2025 | Medium | Conduct annual penetration testing and document findings | 1) Engage penetration testing vendor (Week 1) 2) Conduct testing (Week 2-3) 3) Analyze results (Week 4) 4) Remediate findings (Week 5-8) | CISO | 2026-03-31 | In Progress | Vendor engagement in progress
POA&M-011 | SI-2 | Patch management process documentation incomplete | Low | Complete patch management process documentation | 1) Document current process (Week 1) 2) Identify gaps and improvements (Week 2) 3) Update documentation (Week 3) 4) Train team on new process (Week 4) | DevSecOps Lead | 2026-02-28 | Not Started | Planned for February 2026
POA&M-012 | AC-17 | VPN access logs not integrated with SIEM | Low | Integrate VPN access logs with SIEM for centralized monitoring | 1) Configure VPN log forwarding (Week 1) 2) Create SIEM correlation rules (Week 2) 3) Test and validate (Week 3) 4) Deploy to production (Week 4) | Cloud Infrastructure Manager | 2026-02-15 | Not Started | Planned for February 2026
POA&M-013 | PL-4 | Rules of Behavior not acknowledged by 5 users | Low | Obtain Rules of Behavior acknowledgment from all users | 1) Identify users without acknowledgment (Week 1) 2) Send reminders and follow up (Week 2) 3) Obtain acknowledgments (Week 3) | Compliance Officer | 2026-01-31 | In Progress | Reminders sent
POA&M-014 | SC-7 | AWS WAF rules not optimized for latest OWASP Top 10 | Medium | Update AWS WAF rules to align with OWASP Top 10 2021 | 1) Review current WAF rules (Week 1) 2) Identify gaps vs OWASP Top 10 (Week 2) 3) Implement new rules (Week 3) 4) Test and deploy (Week 4) | Cloud Infrastructure Manager | 2026-02-28 | Not Started | Planned for February 2026
POA&M-015 | MA-2 | Maintenance activity documentation incomplete for Q4 2025 | Low | Complete maintenance activity documentation and improve process | 1) Complete Q4 2025 documentation (Week 1) 2) Review documentation process (Week 2) 3) Implement automated documentation (Week 3) | DevSecOps Lead | 2026-01-31 | In Progress | 70% complete