## SOC 2 Risk Register
Risk ID | Risk Description | Risk Category | Likelihood | Impact | Inherent Risk Score | Risk Owner | Mitigations | Residual Risk | Status
R-001 | AI model drift leading to inaccurate predictions and false positives/negatives | Processing Integrity | Medium | High | 15 | AI Integrity Officer | Automated monthly model retraining, continuous performance monitoring, accuracy thresholds with alerting, model versioning and rollback capabilities | Low | Mitigated
R-002 | Data poisoning attacks compromising training data quality and model integrity | Security | Low | Critical | 15 | AI Integrity Officer | Input validation and sanitization, data quality checks, anomaly detection on training data, immutable Genesis Archive logging | Medium | Mitigated
R-003 | Unauthorized access to sensitive customer data and intelligence analysis | Security | Medium | Critical | 20 | CISO | Multi-factor authentication (MFA), role-based access control (RBAC), least privilege, Genesis Archive audit logging, quarterly access reviews | Low | Mitigated
R-004 | Data integrity compromise through unauthorized modification or deletion | Processing Integrity | Low | Critical | 15 | System Owner | Genesis Archive immutable ledger with cryptographic chaining, automated integrity verification every 24 hours, access controls, audit logging | Low | Mitigated
R-005 | Genesis Archive ledger tampering or integrity violation | Security | Very Low | Critical | 10 | System Owner | Cryptographic chaining (SHA-256), immutable append-only architecture, automated integrity checks, multi-region replication, alerting on violations | Very Low | Mitigated
R-006 | API abuse through excessive requests, scraping, or denial of service | Availability | Medium | Medium | 12 | DevSecOps Lead | Rate limiting per endpoint category, AWS WAF with DDoS protection, API authentication and authorization, monitoring and alerting | Low | Mitigated
R-007 | Insider threat from malicious or negligent employees | Security | Low | High | 12 | CISO | Background checks, least privilege access, separation of duties, Genesis Archive audit logging, user behavior analytics, quarterly access reviews | Low | Mitigated
R-008 | System outage or availability failure exceeding SLA commitments | Availability | Low | High | 12 | Cloud Infrastructure Manager | Multi-AZ deployment, auto-scaling, health checks, automated failover, disaster recovery procedures, quarterly DR testing | Low | Mitigated
R-009 | Correlation engine overload from excessive event volume | Availability | Medium | Medium | 12 | System Owner | Auto-scaling based on CPU/memory, queue-based processing, circuit breakers, performance monitoring, capacity planning | Low | Mitigated
R-010 | Sentinel alert failure or missed critical security events | Security | Low | High | 12 | System Owner | Redundant monitoring with UltraFusion AI, automated health checks every 30 seconds, alert escalation procedures, monitoring validation | Low | Mitigated
R-011 | Encryption key compromise or unauthorized key access | Confidentiality | Very Low | Critical | 10 | Cloud Infrastructure Manager | AWS KMS with HSM, automated key rotation every 90 days, least privilege key access, audit logging, separation of duties | Very Low | Mitigated
R-012 | Third-party dependency vulnerability or supply chain attack | Security | Medium | High | 15 | DevSecOps Lead | Dependency scanning (Dependabot, npm audit), automated security patches within 7 days, SBOM generation, vendor security assessments | Low | Mitigated
R-013 | Privacy breach or unauthorized disclosure of personal data | Privacy | Low | Critical | 15 | Data Protection Officer | Encryption at rest and in transit, access controls, data masking in non-production, Genesis Archive audit logging, privacy training | Low | Mitigated
R-014 | Disaster recovery failure or inability to meet RTO/RPO objectives | Availability | Low | High | 12 | Cloud Infrastructure Manager | Cross-region replication, automated backups every 6 hours, quarterly DR testing with documented results, RTO/RPO validation | Low | Mitigated
R-015 | Compliance violation or audit finding leading to certification loss | Compliance | Low | High | 12 | Compliance Officer | Quarterly control testing, continuous compliance monitoring, audit readiness program, remediation tracking, management review | Low | Mitigated
R-016 | Phishing attack leading to credential compromise | Security | Medium | High | 15 | CISO | Security awareness training, quarterly phishing simulations, MFA enforcement, email filtering, incident response procedures | Low | Mitigated
R-017 | Database performance degradation impacting system availability | Availability | Medium | Medium | 12 | System Owner | Performance monitoring, query optimization, database indexing, auto-scaling storage, capacity planning, alerting on slow queries | Low | Mitigated
R-018 | Change management failure leading to production outage | Availability | Low | High | 12 | DevSecOps Lead | Change Advisory Board (CAB) approval, peer review, automated testing in CI/CD, blue-green deployment, automated rollback, Genesis Archive change log | Low | Mitigated
R-019 | Insufficient logging or audit trail gaps | Security | Low | High | 12 | System Owner | Genesis Archive immutable logging, comprehensive event logging, log retention 7 years, log integrity verification, monitoring for log failures | Very Low | Mitigated
R-020 | UltraFusion AI false positive rate impacting operational efficiency | Processing Integrity | Medium | Medium | 12 | AI Integrity Officer | Confidence scoring (0.0-1.0), tunable thresholds, human-in-the-loop validation, continuous model tuning, feedback loop | Low | Mitigated